|  | THE REPUBLIC OF UGANDA | KAYUNGA DISTRICT LOCAL GOVERNMENT Office of the Senior Community Development Officer P.O.Box 18000 KAYUNGA |
| --- | --- | --- |
| In any correspondence on this subject please quote Date: 20th March, 2018 E-MAIL: caokayunga@hotmail.com, caokayunga@yahoo.com, caokayunga@gmail.com |  |  |

The Chief Administrative Officer,

Kayunga District

Thru: The District Community Development Officer,

Kayunga District

UWEP IMPLEMENTATION STATUS REPORT

Kayunga district is one of the districts that are implementing UWEP program  an interest free financial  credit  to women groups .The program started in FY 2016/2017 with 25 groups being funded reaching out to 402 women in the district.

In the second phase the district submitted 45 women groups and only 7 women groups have been funded and recoveries have not started.

So far the district has so far received 110,958,000/= since inception and so far the district has recovered 20,603,000 and the balance is 90,355,000/= totaling to 27 % of recovery.

In phase 1 some women groups have responded with repayment with Nazigo and Kitimbwa performing well.

Some Groups are still at 0% of recovery

| Sub county | Group Name | Recovery | Remark |
| --- | --- | --- | --- |
| Bbaale | Zibula Atudde | 0 | Groups has conflicts |
|  | Kamu Kamu | 0 | Conflicts in the group |
| Kitimbwa | Muno mu byona | 0 | Reluctant |
| Kitimbwa Kangulumira | Kiddawalime | 300,000 out of 2.5 | Reluctant |
|  | Tusitukile wamu | 400,000 out of 4.8 | Reluctant |
| Kayunga | Nakaseeta catering | 300,000 out of 2.8 | Reluctant |
| Nazigo | Kinyala Coffee nursery | 0 | Nursery bed was attached by pests |
|  | Kisega rice growers | 0 | Yet to harvest |
| KTC | Namagabi B | 0 out of 2.5 | Reluctant |
| Busaana | BESO | 0 out of 5.5 | Project still on going |
|  | Akutwala Ekiro | 400,000 out of 5.5 | Project diversified |

Challenges

- Delay in the realize of funds the MGLSD

- Out of the 46 groups submitted in phase 2 only 7 were funded.

Kawongo Tompita Kulitalaba                      Maize grinding mill      6,000,000/=

Kabaku milk traders and value addition       milk traders                 5,000,000/=

Bwesigwa  Developmen group                     Agro  produce              5,040,000/=

Kayunga Central  Cosmetic trade                Cosmetics selling	       5,000,000/=

Nalumuli  poultry Women project                Poultry                          5,000,000/=

Bukamba town hair dressing group              Hair Dressing               3,000,000/=

Kiwalasi  women  Soft  Drinks  group          Soft drinks selling         4,800,000/=

Total    			        33,444,000/=

- Kinyala Coffee was attached by the pest

- No marketing for art and Crafts projects

Issues noted

- Diversification of projects is a good practice by groups

- Many members in the group leading to conflict.

- We recommend for reduction of members to atleast  5

- Women groups have requested for individual loans as opposed to group loans in UWEP.

Namisi Faridah

Senior Community Development Officer